## Meeting Template
Meeting Date | 2026-01-28
Agenda Item | Attendees
Team Introductions and setting out responsibilities | All team members
Action | Responsible Individual
set out responsibilities for team leader. organize and chair meetings | Asad Jamadar
set out responsibilities for team Secretary. To collect documents and minutes and upload into GitHub repository | Sarmad Anwar
set out responsibilities for team Speaker. Prepare for the presentation when it comes | Ali Najib
Prepare the UI for the prototype | Hassan and Harris
Meeting Date | 2026-02-05
Agenda Item | Attendees
Meeting with the Client and setting out | Client, Harris, Ali, Hassan. Apologies- Sarmad and Asad
Action | Responsible Individual
He presented his prototype model and explained the concept and overall vision behind the project, emphasising its aim to help people save money. He described the initiative as something designed “by the people, for the people,” highlighting its community approach. | All those in attendance
Client said we should choose to do front end or back end or both. It was decided that we would do both | All those in attendance
The client mentioned we should have a login page as this will set us aside from other competitors | All those in attendance
In the future, he expressed interest in integrating a feature that would allow users to upload deals they find in stores, which the system would then verify and add to the platform for others to benefit from. | All those in attendance
Meeting Date | 2026-03-02
Agenda Item | Responsible Individual
Set out responsibilities for all the team in terms of what task the should work on based off the CW1 PDF | All team members
Action | Responsible Individual
Create GitHub Repository and publish meeting minutes | Sarmad
Print off and get signitures for NDA and upload | Sarmad
Contribute to Front end Implementation | All Members
Designed the UI including Login Page and Dashboard pages | Ali/Asad
Implement the backend server functionality for the prototype. Including develop the price comparison logic using mock supermarket data. | Harris
integrate frontend components with backend services. | Harris
Implement and test the functionality of the prototype | Harris/Hassan